## Sheet1
Items | Time Estimates | Estimated Start Date | Actual Time Spen
|  |  | May 6th | May 7th | May 8th | May 9th | May 10th | May 13th | May 14th | May 15th | May 16th | Subtotal | Total Hours
Use Case Diagram | S | 6th | [9 empty] | 1 | 29.15 | bar: Actual Time Spen May 6th
Sequence Diagram for web and iOS | M | 6th | Actual Time Spen May 15th: 0.7 | 0.7
Object Model | S | 6th | Actual Time Spen May 6th: 1.5 | 1.5
Smart Contract | M | 14th | Actual Time Spen May 15th: 1.5 | 1.5
Hardhat Created and Contract Added | S | 14th | Actual Time Spen May 15th: 0.2 | 0.2
Hardhat Test Script | L | 15th | Actual Time Spen May 15th: 2.5 | 2.5
Git Repository for Project | S | 6th | Actual Time Spen May 6th: 1.5 | 1.5
Angular Connect to Wallet | M | 9th | Actual Time Spen May 7th: 0.25 | 0.25
Angular Call Contract Function | M | 16th | [9 empty] | 0
Design and Implement SQL Database | L | 7th | Actual Time Spen May 6th: 0.45; Actual Time Spen May 8th: 0.2; Actual Time Spen May 15th: 1 | 1.65
Express get route | M | 8th | Actual Time Spen May 8th: 0.8; Actual Time Spen May 13th: 1; Actual Time Spen May 15th: 0.4 | 2.2
CSS in Angular | S | 7th | Actual Time Spen May 7th: 0.3; Actual Time Spen May 15th: 0.2 | 0.5
Reusable Component in Angular | S | 7th | Actual Time Spen May 7th: 0.4; Actual Time Spen May 15th: 0.6 | 1
Service in Angular | M | 7th | Actual Time Spen May 7th: 1.5; Actual Time Spen May 9th: 1; Actual Time Spen May 15th: 2 | 4.5
Angular Connection to Express Route | M | 10th | [9 empty] | 1 | bar: Actual Time Spen May 14th
iOS Components | M | 11th | Actual Time Spen May 15th: 2 | 2
iOS Fetch from Express Server | L | 12th | Actual Time Spen May 15th: 3 | 3
Commenting in Code | S | 6th | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 2.7
Folder Management | S | 6th | Actual Time Spen May 6th: 0.25 | 0.25
Reflection Paper on Project | S | 16th | [9 empty] | 1 | bar: Actual Time Spen May 16th
Presentation Video | M | 16th | Actual Time Spen May 16th: 0.2 | 0.2